IR QUARTERLY EXECUTION PLAN

90-Day IR Plan — June 19 to September 17, 2026

Prepared by Paul Manley, SVP Investor Relations · covers the Q2 2026 earnings cycle and the Roth New York conference

| 90 days in this window | 3 key events: blackout, earnings, Roth NY | 2 blocking action items | ~90% of the window is calendar-driven |
| --- | --- | --- | --- |

# Phase 1 — Pre-blackout (Jun 19 – Jul 14)

| Workstream | Action | Owner | Target date | Status |
| --- | --- | --- | --- | --- |
| NOBO | Submit NOBO list request to transfer agent under Rule 14b-1(c); confirm record date | IR / Corp. Secretary | Jul 3 | Open |
| Sell-side | Follow up directly with 5th analyst; confirm continued coverage status | IR | Jun 26 | Open |
| Website | Sign up for visitor-ID tool (Leadfeeder-class) and install tracking script | IR / Web vendor | Jun 30 | Ready |
| Index | Verify Russell Microcap status directly against FTSE Russell's published list | IR | Jun 26 | Open |
| Data maint. | Refresh peer/competitor roster; verify CTLP and IMXI status changes reflected everywhere | IR | Jul 7 | Open |

# Phase 2 — Blackout & earnings (Jul 15 – Aug 7)

| Workstream | Action | Owner | Target date | Status |
| --- | --- | --- | --- | --- |
| Compliance | Blackout opens; all-employee trading window notice auto-fires | IR (auto) | Jul 15 | Set |
| Script | Run “what's new” intake; draft Q2 script weighted on historical archive; counsel review | IR / Counsel | Jul 24 | Set |
| Earnings | Q2 2026 earnings release and call | CEO / CFO | Aug 5 | Set |
| Callbacks | Tiered analyst and shareholder callbacks, post-earnings | CEO / CFO | Aug 5 | Set |
| Compliance | Blackout window reopens | IR (auto) | Aug 7 | Set |

# Phase 3 — Post-earnings & Roth NY (Aug 8 – Sep 17)

| Workstream | Action | Owner | Target date | Status |
| --- | --- | --- | --- | --- |
| Audit | Run post-call audit scorecard (expected vs. actual); re-run market correlation test | IR | Aug 12 | Open |
| Board | Refresh Quarterly IR Board Package and Risk Register with Q2 results | IR | Aug 14 | Open |
| NOBO | Receive NOBO file; build matching logic vs. 13F and website-ID data | IR | Aug 21* | Pending |
| Conference | Roth — New York: meetings list ingestion, prospect flagging, travel calendar sync | IR / CEO | Sep 14–16 | Confirmed |
| Conference | Post-Roth NY follow-up: new contacts added to prospect tracking | IR | Sep 17 | Pending |

*Target date for NOBO receipt is an estimate — actual timing depends on transfer agent turnaround once the request is submitted in Phase 1.

# 90-day outreach targets

| Audience | Target | Mechanism |
| --- | --- | --- |
| Sell-side analysts | 5 of 5 responsive | Model requests + direct 5th-analyst follow-up |
| Top-20 institutional | 12+ callbacks held | Tiered post-earnings callback scheduling |
| NOBO / retail | List received | Transfer agent request — the gating item this quarter |
| New prospects (conference) | 3+ new contacts | Roth NY meeting-list ingestion + website-ID cross-match |

Living document — review and update weekly. Blocking items in red require action within the stated Phase 1 window to avoid delaying downstream Phase 3 work.